## Sheet 1
Date | Action | Details | Comments and follow up | Date Completed | Criterion
21/07/2017 | Interview with the client | Evidence of the interview would be through notes. | Due to the clients lack of english language skills, I translated her statements and propositions. | 21/07/2017 | A
22/07/2017 | Second interview with the client | Questioning more on her attempted solutions and what she needed. | I made a list of the hardware and softwares need to create the finish product | 22/07/2017 | A
23/07/2017 | Preparation of the softwares and hardwares | All the needed softwares and hardwares are gathered | Software: Photoshop, Hardware: preparing the storage and Camera |  | B
27/07/2017 | A schedule is created | The schedule will enable to provide the convince of accomplishing the tasks needed to do | The schedule will be what I will rely on for the whole of the project | 27/07/2017 | C
27/07/2017 | Product Design | Design is created through pages |  | 30/07/2017 | D
28/07/2017 | Learning the codes | The codes that are involved in the finished product based product design |  |  | E
13/08/2017 | Taking Pictures of the products | pictures taken are for the purpose of the thumbnail of the products |  | 15/07/2017 | E
23/08/2017 | Website Development | Templates of the website is already settled |  | 28/07/2017 | E
25/07/2017 | files are gathered and organised |  |  | 30/08/2017 | E
26/07/2017 | Feedbacks |  |  |  | F
28/08/2017 | Video record |  |  | 31/07/2017 | G
Criterion C: Project schedule